## Sheet1
| Latest Due | done
Required Hardware Setup:
LCD Setup and test Draw | 2015-03-02
LCD Print Text with scaling | 2015-03-02
LCD copy Image to location | 2015-03-02
Output menu object | 2015-03-12
Recieve Inputs | 2015-03-13
Test and Verify MenuObject | 2015-03-14
Start mario gameobject | 2015-03-15
one image | 2015-03-15
changes direction | 2015-03-15
animated | 2015-03-16
SD card accessing image files | 2015-03-19
make array of "memory cache" uint16_t pointers with defined MAX_CACHED_OBJECTS (eg 255) | 2015-03-20
#define every objects size, when object laoded to cache offest each pointer and assign value to "memory cache" | 2015-03-20
each gameobject, in lieu of a pointer to the direct memory location, they have a relative pointer to the index of that "memory cache" array, who cointains the actual pointer to the datas | 2015-03-20
this simple alloc scheme works for more than just images for gameobjects, can cache music etc, as long as whatever needs that data has the relative pointer
SD card reading image files into a cache slot | 2015-03-21
change Mario to use cache slotted/SD card system | 2015-03-21
on creation copies image from sdcard to cache slot and adds "mario size" to "next pointer" | 2015-03-21
stores pointer in mario (incs static global keeping track of what cache slot is used) | 2015-03-21
render function changed pointer style | 2015-03-21
deconstruction decrements static global cache slot and subtracts "mario size" from "next pointer" | 2015-03-21
play music by caching entire song and playing | 2015-03-22
on rising edge sending until IRQ low send data from buffer until low | 2015-03-23
when low fill buffer up | 2015-03-23
exit IRQ | 2015-03-23
LATER: rising edge IRQ of DR sends byte, SPI complete IRQ checks DR and sends another byte if necessary
make music play when game running | 2015-03-25
make music change for each sub menu of game | 2015-03-26
get touch inputs | 2015-03-27
touch draw points | 2015-03-28
Touch screen paint that exits on button press | 2015-03-28
Start DMAing inputs | EXTRA
Start DMAing the music spi from buffer | EXTRA
start DMAing the SD card | EXTRA
start DMAing the images with DMA2D for rendering | EXTRA
start DMAing the characters for drawText with DMA2D | EXTRA
Swap "pallete" with cartridge
bootloader